## Sheet1
sr no | date | what task assign | estimate | when I did complate
1 | 2024-04-29 | see project stucture | 1 day | 1 day
2 | 2024-04-30 | make sign up form ui | 1 day | 1day
3 | 2024-05-02 | apply validation | 1day | 1day
4 | 2024-05-03 | make password and confirm pwd | 1 day | 1 day
5 | 2024-05-06 | make dashboard ui and functinality |  | 2 day
6 | 2024-05-07 | make dashboard ui and functinality |  | 2 day
7 | 2024-05-08 | in dashboad added like and routing | 1 day | 1 day
8 | 2024-05-09 | created five component and working on product list |  | 2 day
9 | 2024-05-10 | product list ui done and 13 -05-2024 on leave |  | 2 day
10 | 2024-05-14 | add and edit component create form field work from home | 1 day | 1 day
11 | 2024-05-15 | do category and subcategory functionality and all field to apply validation | 1 day | 1 day
12 | 2024-05-16 | work on preview functionality | 1 day | 1 day
13 | 2024-05-17 | edit and add component ui and functionality and all correction do |  | 1 day
14 | 2024-05-20 | add dialog box with functionality preview add and addevent to to show data to link when mobile screen show |  | 1 day
15 | 2024-05-21 | make edit component responsive |  | 1 day
16 | 2024-05-22 | add popup delete and edit and it reusable | 1 day | 1 day
17 | 2024-05-23 | add dialog to creation component,list product search functionality,create product view component and routing and product ui done and create profile component and make routing | no | 1 day
18 | 2024-05-24 | creating a profile page ui |  | 1 day
19 | 2024-05-27 | changes button text color | no | 1 day
20 | 2024-05-28 | make category component and make routing and make table with search bar and add button | no | 1 day
21 | 2024-05-29 | do validation edit and add and fixed pagination userlist and orderlist and what can improve | no | 1 day
22 | 2024-05-30 | image,checkbox validation do | no | 1 day
23 | 2024-05-31 | make routing customer view comp and customerview fixed and make responsive and profile and product details fixed scrollbar and width | no | 1 day
2024-06-01
1 | 2024-06-03 | make navlink dashboad and it conditionly render then add content as card and make it responsive | no | 1 day
2 | 2024-06-04 | make profile menu list profile and logout and add icon on dashboard and fixed ipad mini sized | no | half day
3 | 2024-06-05 | fixed button add & edit component in dashboard card icon title and add menu design and conditionaly render the proper value | no | 1 day
4 | 2024-06-06 | make another 4 card different design and first card in one row and other are 1 row 2 card | no | 1 day
5 | 2024-06-07
6
7
8
9
10
11